## Slide 1: CS428: Software Engineering II
Planning and Risks

## Slide 2: Today’s goals
How should we plan and schedule activities in a software project?
What are the biggest risks in a software project? How can we mitigate them?

## Slide 3: Project proposal parts
Description
Motivation
Comparison with similar software
Languages, libraries, frameworks, platforms
Risks/challenges
User stories and iterations
Meeting schedule (6+ hours/week of work)
Skill sets
Process
Tools
Related projects, if any

## Slide 4: Planning in XP
Planning Game
Customer / Developer
User stories, estimates
Iteration planning meeting
Recall lecture contents on planning in XP in CS427

## Slide 5: How to plan
Make a list of everything you have to do
Decide when you will do each thing
  How long will it take?
Make sure you have what you need for each task

## Slide 6: How long will it take?
Compare with other tasks you have done
If too hard to estimate, break into smaller steps
Get several people to estimate

## Slide 7: Scheduling
Determine list of tasks
Determine needed resources for each task
  People
  Computers, testing system
Schedule tasks
  Some tasks depend on others
  Some tasks compete for resources

## Slide 8: Program Evaluation and Review Technique (PERT)
Model for project management and planning
Represent tasks and their dependencies
Estimate amount of time for each task
Compute the time for entire project
http://en.wikipedia.org/wiki/Program_Evaluation_and_Review_Technique
  How to compute the critical path?

## Slide 9: PERT example
Critical path - path that takes longest
Slack - extra time for task
Only optimize steps on critical path
Develop parser
Develop type checker
Develop code generator
Define ASTs
0
5
3
8
9
17
14
6
11
Integrate
3
3
3
14
3

## Slide 10: Gantt charts
http://en.wikipedia.org/wiki/Gantt_chart
http://www.gantt.com/creating-gantt-charts.htm
You may use Google doc following a template, e.g., https://drive.google.com/templates?q=gantt&ddrp=1#

## Slide 11: Gantt charts
http://en.wikipedia.org/wiki/Gantt_chart
http://www.gantt.com/creating-gantt-charts.htm
Start to Start (SS): The task cannot start until the predecessor starts, although it may start later.
Finish to Finish (FF): The task cannot end before the predecessor ends, although it may end later.
You may use Google doc following a template, e.g., https://drive.google.com/templates?q=gantt&ddrp=1#

## Slide 12: Exercise
Your project has two phases. Each phase consists of three main tasks: analysis, coding and test, which must be performed sequentially.
Analysis for phase 2 can begin immediately on the completion of analysis for phase 1, but coding for phase 2 must await satisfactory testing of the phase 1 code.
Analysis is expected to take 3 weeks for phase 1, and 4 weeks for phase 2, while coding is expected to take 2 weeks for phase 1 and 3 weeks for phase 2. Testing is expected to take 1 week for both phases.
Adapted from https://www.cl.cam.ac.uk/teaching/1011/Business/Examples.pdf
Draw the PERT and Gantt charts for the project, and define the critical path.
During testing of phase 1, a serious fault is found resulting in 2 weeks of extra work required in phase 1. How will this affect the overall timescale and critical path of the project?

## Slide 14: Project tracking
Keep track of when each task is finished
Compare plan to reality
  Project: You will update Wiki for your project
Tasks are either finished or not
Forbid “90% finished” - decompose tasks
  XP is strict on this but you can modify XP

## Slide 15: Schedule
List of dates, and the tasks to be finished (or started) at each
  Can put into a spreadsheet
  Task & date, sorted by date
  Separate column for actual completion date
  Project: Can present on Wiki as a table (part of your Planning Game)

## Slide 16: When is a task finished?
Must be objective
  “Wrote a program” not “Learned language”
  “Design passed review” not “Design is reusable”
Different tasks are evaluated differently
  In XP, a programming task is not finished until all tests run correctly
  In RUP, writing a document is a separate task from reviewing it
Example tools: Trello (https://trello.com/)
  See optional reading on Trello in schedule page

## Slide 17: Risks
From Sommerville Ch. 22 (see Wiki)
Project risks
Product risks
Business risks
Recall lecture contents on risk (management) in CS427

## Slide 18: What can go wrong?
Problem harder than we thought
We waste time, take too long
Customers don’t know what they want
System is too slow
Stock options become worthless, developers quit
Developers get bored and quit
Developers like new technology. It doesn’t work
Customers run out of money and kill the project

## Slide 19: Risk management process
Projects get killed for same old reasons
Use database of problems to identify risk
Assess risks
Avoid risks. Contain. Mitigate
Monitor risks you can’t avoid

## Slide 20: Biggest risks in your opinion?
Process should address biggest risks

## Slide 21: Some biggest risks in SW
Process should address biggest risks
  Wrong requirements
  Constantly changing requirements
  Inadequate schedule

## Slide 22: How to manage biggest risks
Process should address biggest risks
  Wrong requirements
    Iterative development
    Work closely with customer
  Constantly changing requirements
    Manage changes
    Keep schedule up to date
  Inadequate schedule
    Keep schedule up to date
    Reduce scope

## Slide 23: Risk management
Risk assessment: a document listing risks, their likelihood, and their severity
Decide whether you are going to try to avoid this risk or just to monitor it

## Slide 24: Risks in your own projects?
What are risks in academic software engineering projects (as opposed to real world software project)?

## Slide 25: Managing risk in XP
Iteration
Do the simplest thing that could possibly work
Customer picks most important stories
Developers estimate time
  Stories they can’t estimate (or that have long estimates) are risky; developers must work (prototype) to make reliable estimate

## Slide 26: Different types of risk (1)
Risk: later iterations need more sophisticated design than first ones
  XP: keep design clean and simple and change it if necessary
  RUP: elaboration phase should consider all use cases and should select ones that are risky to do first

## Slide 27: Different types of risk (2)
Risk: As developers leave the project, new developers must learn the system
  XP: Use pair programming to teach new developers the system and to make sure that knowledge of the system is spread as widely as possible
  RUP: Document the architecture and key use cases

## Slide 28: Why people don’t manage risk?
Don’t be a negative thinker!
Don’t raise a problem unless you have a solution for it
Don’t say something is a problem unless you can prove it is
Don’t raise a problem unless you want to be responsible for solving it

## Slide 29: Discovering risks
Think of catastrophic outcomes: “What is your biggest fear?”
Scenarios
Root causes

## Slide 30: Management tips for teams
Assign a project manager
Have a single person responsible for each item
  “If everyone is responsible, no one is responsible” (but collective code ownership)
Have a plan (agenda) for each meeting
Make everything public
  Plans, actuals, metrics, …